## Project Planner
Project Planner |  |  | Plan Duration |  | Actual Start |  | % Complete |  |  | Over due
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks (Starting from 28/03/20)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Design & Requirements
Requirements of Users | 1 | 1 | 1 | 1 | 100%
Gantt Chart | 1 | 1 | 1 | 1 | 100%
Planning and Designing | 2 | 1 | 2 | 1 | 100%
Implementation
Coding and Validating | 3 | 3 | 3 | 1 | 100%
Testing & Evaluation
Demonstration of Application | 6 | 2 | 6 | 2 | 100%
Black Box Testing | 6 | 2 | 6 | 2 | 100%
Critical Evaluation | 6 | 2 | 6 | 2 | 100%
Weeks (Ending on 14/05/20)